## Planning
Project Overview | [10 empty] | Estimate |  |  |  |  | Actual (In Progress)
Project | 3D Scanning Masterclass |  |  | Vendor | Jeffrey Ian Wilson |  |  | Kickstarter |  | 6295 | LoE - Capture | 33 | Compute Hrs |  | 176 | LoE - Capture |  | 38 | Compute Hrs |  | 0
Subject | George Air Force Base |  |  | Contact | jeffrey_ian_wilson@hotmail.com |  |  | Software & Hardware |  | -5434.83 | LoE - Processing | 168 | Compute Rate |  | 20 | LoE - Processing |  | 8 | Compute Rate |  | 10
Doc Date | 2024-07-21 |  |  | Client | Jeffrey Ian Wilson |  |  | Admin, Legal, Labor |  | -2300 | Rate per hour | 150 | Compute Total |  | 3520 | Rate per hour |  | 150 | Compute Total |  | 0
Scan Date | Fall 2024 |  |  | Contact | jeffrey_ian_wilson@hotmail.com |  |  | Balance |  | -1439.83 | Total + 10% | 34672.5 | Grand Total |  | 38192.5 | Total + 10% |  | 7590 | Grand Total |  | 7590
Personal Hardware & Software Inventory | [10 empty] | Planned Delivery Items & Estimated Level of Effort
Item |  |  | Qty | MSRP | Rental | Weeks | Months | Actual | Notes |  | Item |  | Qty | Drone | PGM | Lidar | SLS | TotalCx | Proc | TotalPx | Compute | TotalCp
2023 Dell Alienware M18 laptop |  |  | 1 | 5500 |  |  |  | 0 | heat issues |  | Intro - Smart Phone 3DS |  | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4 | 0
2022 Apple iPhone 14 Pro Max 1tb |  |  | 1 | 1250 |  |  |  | 0 |  |  | Intro - HDR / 360 |  | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0
2022 DJI Osmo Mobile 6 Gimbal |  |  | 1 | 600 |  |  |  | 0 |  |  | Intro - Drone |  | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0
2024 Calibrite Color Checker Classic |  |  | 1 | 79 |  |  |  | 0 |  |  | Intro - Lidar |  | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 4 | 0
2024 Printed Lidar & PGM Targets |  |  | 30 | 20 |  |  |  | 0 |  |  | Intro - Appearance |  | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 1 | 0
2024 Hardback Folio |  |  | 1 | 15 |  |  |  | 0 |  |  | Intro - SLS |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0
Agisoft Metashape Pro 2.1 - Education |  |  | 1 | 500 |  |  |  | 0 |  |  | Intro - Nerf/Splats |  | 0 | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 8 | 0
Microsoft Office & One Drive |  |  | 1 | 199.99 |  |  |  | 199.99 | per year |  | Aerial Site Survey |  | 1 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 16 | 16
Adobe Creative Cloud |  |  | 1 | 0 | 59.99 |  | 12 | 719.88 |  |  | Building - Small - Exterior |  | 5 | 1 | 1 | 1 | 0 | 15 | 16 | 80 | 16 | 80
Adobe Substance |  |  | 1 | 0 | 19.99 |  | 12 | 239.88 |  |  | Building - Small - Interior |  | 5 | 0 | 1 | 1 | 0 | 10 | 16 | 80 | 16 | 80
Epic Games Reality Capture 1.4 |  |  | 1 | 0 |  |  |  | 0 |  |  | Prop Scans |  | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 1 | 0
Epic Games Unreal Engine 5.4 |  |  | 1 | 0 |  |  |  | 0 |  |  | Material Scans |  | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 0
Blender 4.2 LTS |  |  | 1 | 0 |  |  |  | 0 |  |  | HDRI Capture |  | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0
Alicevision Meshroom |  |  | 1 | 0 |  |  |  | 0 |  |  | Totals |  | 11 | 11 | 12.5 | 6 | 2 | 33 | 68.25 | 168 | 75.25 | 176
Cloud Compare |  |  | 1 | 0 |  |  |  | 0
TutorLMS Pro |  |  | 1 | 199 |  |  |  | 199 | per year |  | Actual Delivery Items & Level of Effort (In Progress)
Dreamhost Website Hosting |  |  | 1 | 0 | 35 |  | 12 | 420 |  |  | Item |  | Drone | PGM | Lidar | Ref | TotalCx | Proc | Compute | Notes
Samsung 4tb USC 3.2 SSD |  |  | 1 | 613 |  |  |  | 302 |  |  | Aerial Site Survey 01 (6/22/2024) |  | 4 | 0 | 0 | 4 | 8 | 0 | 0 | Drone
Qoocam Ultra 3 & Extra Battery |  |  | 1 | 924 |  |  |  | 621 |  |  | 3DSM Scan 01 (9/21/2024) |  | 4 | 4 | 6 | 2 | 16 | 0 | 0 | 7 Navvis, Qoocam and Mavic3E
iFootage Cobra 3 Monopod |  |  | 1 | 329 |  |  |  | 193.99 |  |  | 3DSM Scan 02 (9/28/2024) |  | 0 | 2 | 0 | 0 | 2 | 0 | 0 | iPhone, too hot
ScanDisk Extreme 512gb MicroSD & Reader |  |  | 1 | 329 |  |  |  | 53 |  |  | 3DSM Scan 03 (10/19/2024) |  | 0 | 4 | 4 | 0 | 8 | 0 | 0 | BLK360, DSLR
Ptgui Pro |  |  | 1 | 776 |  |  |  | 0 |  |  | 3DSM Scan 04 (10/20/2024) |  | 4 | 0 | 0 | 0 | 4 | 0 | 0 | Drone
EasyHDR |  |  | 1 | 65 |  |  |  | 0 |  |  | Scan Processing |  | 0 | 0 | 0 | 0 | 0 | 8 | 0
Zoom Workspace Pro |  |  | 1 | 0 | 15.99 |  | 12 | 191.88
Trello Premium Standard |  |  | 1 | 0 | 119.99 |  | 12 | 119.99 | per year
Pix4D Catch / Cloud Subscription |  |  | 1 | 0 | 59.99 |  | 3 | 179.97
Prexio Laser Tape Measure & Rangefinder |  |  | 1 | 86.18 | 0 |  |  | 86.18
Razer Kraken Headset |  |  | 1 | 300 | 0 |  |  | 193.94
Smallrig iPhone DSLR Shoe Mount |  |  | 1 | 20 | 0 |  |  | 20
IM150 Wireless Light and Color Meter |  |  | 1 | 376.05 | 0 |  |  | 376.05
Discord Nitro |  |  | 1 | 0 | 9.95 |  | 12 | 119.4
Microsoft OneDrive +1tb storage |  |  | 1 | 0 | 9.99 |  | 12 | 119.88
CVS - Masks, Glue, First Aid |  |  | 1 | 60 | 0 |  |  | 60 |  |  | Totals |  | 12 | 10 | 10 | 6 | 38 | 8 | 0
Cloudflare R2 Storage |  |  | 1 | 0 | 34.95 |  | 12 | 419.4
Jetpack Complete |  |  | 1 | 0 | 599.4 |  | 1 | 599.4 | per year |  | Estimated Image Count |  |  |  | Estimated Lidar Count
Total |  |  |  | 11398.99 |  |  |  | 5434.83
[11 empty] | Sensor | MegPix | Count | GigPx | Sensor |  | ImgCount | GigPx | Mpts
Project Hardware & Software Inventory | [10 empty] | DJI Mavic 3E JPG | 20.89 | 5000 | 104.45 | BLK360
Item |  |  | Qty | MSRP | Rental | Weeks | Months | Total | Actual | Notes | DJI Mavic 3E DNG | 20.89 | 2500 | 52.225 | RTC360
2023 Lenovo P620 Workstation |  |  | 1 | 16000 |  |  |  | 0 | 0 | Sponsored | iPhone 14 Pro JPG | 12 | 5000 | 60 | BLK2Go
SideFX Software Houdini FX |  |  | 1 | 4495 |  |  |  | 0 | 0 | Sponsored | iPhone 14 Pro DNG | 48 | 2000 | 96 | Navvis VLX3
Agisoft Metashape Pro |  |  | 1 | 3500 | 0 |  |  | 0 | 0 | Sponsored | Qoocam Ultra 3 DNG | 96 | 2000 | 192 | Navvis MLX
3D Flow Zeyphr |  |  | 1 | 3500 | 0 |  |  | 0 | 0 | Sponsored | Qoocam Ultra 3 JPG | 96 | 3000 | 288
Volinga Desktop |  |  | 1 | 0 | 0 |  |  | 0 | 0 | Sponsored | Sony A7r3 ARW | 42.2 | 2000 | 84.4
Sony A7R3 DSLR |  |  | 1 | 3500 | 500 | 2 |  | 1000 | 0 | Loaner | Total |  | 21500 | 877.075 | Total
Sony 28mm Lens |  |  | 1 | 2500 | 250 | 2 |  | 500 | 0 | Loaner | Actual Image Count |  |  |  | Actual Lidar Count
DJI Mavic 3E Enterprise with RTK |  |  | 1 | 6800 | 710 |  |  | 0 | 0 | HydraFX | Sensor | MegPix | Count | GigPx | Sensor |  | ImgCount | GigPx | Mpts
Emlid RS2+ GNSS |  |  | 1 | 2500 | 0 |  |  | 0 | 0 | HydraFX | DJI Mavic 3E JPG | 20.89 | 3257 | 68.0387 | BLK360 |  | 38 | 2.28
Leica RTC360 Lidar |  |  | 1 | 75000 | 3500 | 1 |  | 3500 | 0 | Not Used | DJI Mavic 3E DNG | 20.89 | 2995 | 62.5656 | Navvis VLX3 |  | 5756 | 114.8898 | 772.9
Leica BLK360g2 Lidar |  |  | 1 | 18500 | 2000 | 1 |  | 2000 | 0 | Sponsored | iPhone 14 Pro JPG | 12 | 0 | 0 | Navvis MLX |  | 3056 | 37.5888 | 109.1
Leica Cyclone Register 360 |  |  | 1 | 4750 | 370 |  | 3 | 1110 | 0 | Sponsored | iPhone 14 Pro DNG | 48 | 0 | 0
Leica Reality Cloud Studio |  |  | 1 | 0 | 425 |  | 3 | 1275 | 0 | Sponsored | Qoocam Ultra 3 DNG | 96 | 685 | 65.76
Artec Leo |  |  | 1 | 34000 | 650 |  | 1 | 650 | 0 | Sponsored | Qoocam Ultra 3 JPG | 96 | 400 | 38.4
Artec Studio |  |  | 1 | 0 | 100 |  | 12 | 1200 | 0 | Sponsored | Sony A7r3 ARW | 42.2 | 874 | 36.8828
Total |  |  |  | 175045 |  |  |  | 11235 | 0 |  | Total |  | 8211 | 271.6471 | Total |  | 8850 | 154.7586 | 882
Labor & Misc Expenses
Name |  | Contact |  |  | Rate | Units | Total | Actual | Notes
Jeffrey Wilson |  | jeffrey_ian_wilson@hotmail.com |  |  | 90 | 201 | 18090 | 0 | Estimate
HydraFX |  | lee@hydrafx.com |  |  | 1500 | 2 | 3000 | 600 | Aerial survey (6/22), flat rate, trade
Scan Tech |  |  |  |  | 30 | 10 | 300 | 300 | Paid (9/21 - 10/19)
Wordpress Designer |  |  |  |  | 30 | 24 | 720 | 720 | Estimate
Accountant |  |  |  |  | 300 | 1 | 300 | 300 | Paid
Permit |  | Lily Franco (lfranco@victorvilleca.gov) |  |  | 0 | 1 | 0 | 0 | No charge, trade data to SCLA
Liability Insurance |  | Eventsured |  |  | 205 | 1 | 205 | 205 | Paid (9/21 - 10/19)
Meals & Misc |  |  |  |  | 175 | 1 | 175 | 175
Total | [6 empty] | 22615 | 2300

## Scan Captures
Scan Captures - June 2024 |  |  |  |  | Scan Captures - September 2024 |  |  |  |  | Scan Captures - October 2024
Aerial Survey 01 |  |  |  |  | AOI Scan 01 |  |  |  |  | AOI Scan 03
Project | 3D Scanning Masterclass |  | Lead | Jeffrey Ian Wilson | Project | 3D Scanning Masterclass |  | Lead | Jeffrey Ian Wilson (Qoocam) | Project | 3D Scanning Masterclass | Lead | Jeffrey Ian Wilson
Subject | George Air Force Base |  | Scan Tech | Lee Mar - HydraFX (drone) | Subject | George Air Force Base |  | Scan Tech | Lee Mar - HydraFX (drone) | Subject | George Air Force Base | Scan Tech | Roman Materna
Scan | Aerial Survey 01 |  | Scan Tech | Roman Materna (reference) | Scan | AOI Scan 01 |  | Scan Tech | Noah Eckhous (Navvis) | Scan | AOI Scan 03 | Scan Tech
Date | 2024-06-22 |  | Scan Tech |  | Date | 2024-09-21 |  | Scan Tech | Roman Materna (Ref/Navvis) | Date | 2024-10-19 | Scan Tech
Time | 7-8 hrs onsite |  | Actual Tx | 4 hours | Time | 7-8 hrs onsite |  | Actual Tx | 6.5 hours | Time | 7-8 hrs on site | Actual Tx
Details |  |  |  |  | Details |  |  |  |  | Details
George AFB housing and environment |  |  |  |  | George AFB housing enclosure |  |  |  |  | DSLR & BLK360 capture
Mavic 3 Enterprise RTK with GNSS Ground Control |  |  |  |  | Mavic 3 Enterprise RTK with GNSS Ground Control |  |  |  |  | Focus on one house exterior & interior
JPG capture due to area size and length of capture |  |  |  |  | Nadir & Oblique Imagery, GSD 1cm, DNG Capture, Flight Time?
3 hrs total flight time, 8,000 images expected, GSD of 1-2cm/pixel |  |  |  |  | Navvis VLX 3, Qoocam Ultra 3
iPhone 14 Pro Reference Images & Test Scan of House |  |  |  |  | iPhone 14 Pro & DSLR Reference Images
Documentation, reference images |  |  |  |  | Documentation
Additonal DSLR & drone reference captures if time permits
Agenda |  |  |  |  | Agenda |  |  |  |  | Agenda
7:30 | Arrive Onsite |  |  |  | 7:30 | Arrive Onsite |  |  |  | 9:00 | Arrive Onsite
8:00 | Find Established Point |  |  |  | 8:00 | Mark / Observe GCPs |  |  |  | 9:30 | Gear Check & Testing
9:30 | Mark / Observe GCPs |  |  |  | 9:00 | Gear Check & Testing |  |  |  | 10:00 | Scan Session 01
10:30 | Drone Exposure Check / Scanning |  |  |  | 10:00 | Scan Session Begins |  |  |  | 12:00 | Break for Lunch
12:30 | Aerial Survey Finished |  |  |  | 14:00 | Scan Session Ends |  |  |  | 1:00 | Scan Session 02
13:00 | Drone Scan - Water Tower |  |  |  | 14:30 | Wrap Onsite Work |  |  |  | 4:00 | Wrap Onsite Work
14:00 | Wrap onsite work |  |  |  | 15:00 | Lunch / Data Download & Review |  |  |  | 5:00 | Data Download & Review
15:00 | Data download and review
Capture Outcomes |  |  |  |  | Capture Outcomes |  |  |  |  | Capture Outcomes
Time |  | Weather onsite limited capture time to 4 hours |  |  | Time |  | Capture completed on schedule 10am - 2pm
GNSS GCPs |  | GNSS GCPs captured for entire region |  |  | GNSS GCPs |  | 19 GCPs captured
RTK Issues |  | Could not consistently get RTK connection in center of AOI |  |  | Oblique Missions |  | Only 2 oblique missions completed due to batteries & time
WB Issues |  | Camera Firmware causes WB issues with presets (auto and custom K) |  |  | Weather |  | Sunny and clear, temps reached into low 90s F
JPG |  | JPG captured due to time limitations (3,250) |  |  | AOI |  | Multiple AOIs captured
Weather |  | Heat became unbearable by noon, causing heat exhaustion for 2
AOI |  | Limited capture area with 3,250 images and 3cm GSD
Outcome |  | Return and conduct another aerial survey addressing above |  |  | Outcome |  | Return for remaining 2 drone oblique missions |  |  | Outcome
[5 empty] | AOI Scan 02 |  |  |  |  | AOI Scan 04
[5 empty] | Project | 3D Scanning Masterclass |  | Lead | Jeffrey Ian Wilson | Project | 3D Scanning Masterclass | Lead | Jeffrey Ian Wilson
[5 empty] | Subject | George Air Force Base |  | Scan Tech |  | Subject | George Air Force Base | Scan Tech | Lee Mar - HydraFX
[5 empty] | Scan | AOI Scan 01 |  | Scan Tech |  | Scan | AOI Scan 03 | Scan Tech
[5 empty] | Date | 2024-09-28 |  | Scan Tech |  | Date | 2024-10-20 | Scan Tech
[5 empty] | Time | 2 hr |  | Actual Tx | 1 hr | Time | 4 hrs on site | Actual Tx
[5 empty] | Details |  |  |  |  | Details
[5 empty] | Test iPhone 14 Pro Survey Points in Pix4D Catch |  |  |  |  | DJI M3E DNG Capture of 2 Obliques
Pix4D Catch capture of AOI Survey points
[5 empty] | Agenda |  |  |  |  | Agenda
[5 empty] | 1:00 | Capture Pix4D Catch GCPs with iPhone |  |  |  | 9:00 | Arrive Onsite
[5 empty] | 1:30 | iPhone 14 Pro Max Pix4D Scan of AOI crossroads and existing GCPs |  |  |  | 9:30 | Gear Check & Testing
[5 empty] | 2:00 | Wrap |  |  |  | 10:00 | Scan Session 01
[10 empty] | 2:00 | Wrap Onsite Work
[10 empty] | 3:00 | Data Download & Review
[5 empty] | Capture Outcomes |  |  |  |  | Capture Outcomes
Time
[5 empty] | GNSS GCPs |  | Pix4D Catch w/iPhone 14 Pro Max
[5 empty] | Weather |  | Clear and Sunny, 101f
[5 empty] | AOI |  | Crossroads & AOI GCPs
[5 empty] | Outcome |  |  |  |  | Outcome

## Estimates & Benchmarks
Large Scale Processing Estimate Calculator
Camera | Images | Mpx | Size(mb) | Gpx | Price/Gpx | Size(tb) | Total
Mavic 3E Wide JPG | 3257 | 20.89 | 18 | 68.0387 | 15 | 0.058626 | 1020.581
Mavic 3E Wide DNG | 2995 | 20.89 | 43 | 62.5656 | 15 | 0.12879 | 938.4832
Qoocam Ultra 3 DNG | 685 | 96 | 188 | 65.76 | 10 | 0.12878 | 657.6
iPhone 14 Pro JPG | 0 | 12 | 4 | 0 | 10 | 0 | 0
iPhone 14 Pro DNG | 0 | 48 | 35 | 0 | 10 | 0 | 0
Sony A7r3 ARW | 875 | 42.2 | 72 | 36.925 | 10 | 0.063 | 369.25
Totals | 7812 |  |  | 233.2893 |  | 0.37919 | 2985.9142
Point Cloud | Images | Mpx | Size(mb) | Gpx | Price/Gpt | Size(tb) | Total
Navvis VLX3 | 1185 | 52 | 200 | 616.2 | 50 | 0.237 | 30810
Navvis MLX | 3 | 52 | 201 | 1.56 | 50 | 0.000603 | 78
Leica BLK360g2 | 38 | 60 | 500 | 22.8 | 25 | 0.5 | 570
Leica RTC360 | 0 | 200 | 200 | 0 | 50 | 0.2 | 0
Leica BLK2Go | 0 | 24 | 50 | 0 | 50 | 0.05 | 0
Totals | 1226 |  | 901 | 640.56 |  | 0.7376 | 31458
Task | Gpx/Day | Time/Days |  |  | Subtotal |  | 34443.9142
Image Processing | 3000 | 0.077763 |  |  | Overhead | 10% | 3444.3914
Photogrammetry | 207.49 | 1.1243 |  |  | Project Initiation Fee |  | 1000
Lidar? |  | 3 |  |  | Total |  | 38888.3056
Post | 5 | 5 |  |  | Hardware & Software |  | 0
Transfer | 1 | 1 |  |  | Labor |  | -3188.1572
Total Days + Overhead | 25% | 12.7526 |  |  | Balance |  | 35700.1484
P620 128gb 64core A5500 Benchmarks
GeorgeAFB Aerial Survey #1 (High Structure)
Metashape Pro | Time (Days) | Hours
Align (Highest 80/20) | 0.03125 | 0.75
Depth Maps (High) | 0.10417 | 2.5
Mesh Blocks (250m/Low) | 0.088333 | 2.12
Texture (0.017/0.03m GSD) | 0.10417 | 2.5
Total | 0.32792 | 7.87
Gpx | 68.04
Gpx/Day | 207.4917
Reality Capture | Time (Days) | Hours
Align (Highest 80/20) | 0.027917 | 0.67
Depth Maps (High) | 0.05 | 1.2
Meshing (Normal / 10%) | 0.03125 | 0.75
Texture (0.017/0.03m GSD) | 0.051667 | 1.24
Total | 0.16083 | 3.86
Gpx | 68.04
Gpx/Day | 423.0466